## ReadmeFirst
Department of Climate Change, Energy, the Environment and Water (DCCEEW), NSW
Planting Plan Workbook - Instructions
To be used when completing your planting plan for your Living Carbon grant application.
About this Workbook
This planting plan workbook contains blank and pre-formatted versions of each table that you need to complete in your planting plan. It is recommended that you fill out each table in the workbook, specifically those containing formulas. You can then copy and paste the completed tables into your planting plan. Note: When copying and pasting tables from the workbook into your planting plan, only copy over the contents and not the formulas. Do this by: 1. selecting/highlighting the completed table in the workbook 2. right click and select ‘Copy’ 3. go your planting plan, place the cursor where you want to paste/insert the table and right click on it, 4. select “Paste Special” 5. select the first icon on the left to “Keep Source Formatting (K)” There is one sheet (the coloured tabs at the bottom) for every section of your planting plan except for the schedules/timelines which are divided across two sheets. See the sections and their corresponding tables below.
| Guide Section | Worksheet tab | Tables included
| Section 3 | 3_CarbonProject | Table A - Planting sites and properties/characteristics.
| Section 4 | 4_ProjectActivities | Table B to Table F - Planting method, Site preparation, Fencing, Planting materials, Maintenance and reporting Also, Admin (optional for workbook budget only)
| Section 5 | 5_TargetCobenefits | Table G to Table I -Target co-benefits; Species list, diversity and abundance of predicted species to be planted; Summary of planting diversity and abundance
| Section 7 | 7_Time0to18mths 7_ProjectDelivery | Table K - Project schedule for 18 months of the Living Carbon grant Table L and Table M - Project schedules for 1 to 5 years and 6 to 25 years
| Section 8 | 8_Budget 0_Contractor | Budget overall Optional for applicant only to record contractors
Instructions
> Follow the prompts at the top of each sheet and in the guide to complete the workbook. > Parts of the workbook that contain formulas or drop down menus are locked, which means you can not change them. This is to prevent you accidnetally deleting them. > You can add rows to all tables except the 8_Budget sheet, you can not add columns > If you are unsure of why some cells become automatically shaded or what an error messsage means, refer to Workbook rules below.
Disclaimer: using this workbook is optional, not mandatory. The workbook will not be submitted as part of the Living Carbon grant application. All efforts have been made to ensure formulas and figures in the workbook deliver accurate figures. However, we do not guarantee the accuracy of the numbers and we expect anyone using it to double-check their numbers prior to including them in the planting plan.
Applicants do not need to read or review this. It has been noted here, out of interest and so that you can see what the rules are if you use the Worbook long term.
Sheet | Column(s) | Type | Rule | Explanation
4 Project Activities | A and F | Format | If "Weed Control" or "Other" is entered into a cell in column A "Activity", then the cell on the same row in column F "Grant", will go grey. | Grant funds can not be used for weed control or other activities.
4 Project Activities | A, E, F | Message "please change" | If "Weed Control" or "Other" is entered into a cell in column A "Activity", and a number more than $0 is entered into column F "Grant", then this message will appear "Please change grey cell to N/A: because weed control and other is inelgibile grant expenditure" | You can not use grant funds to pay for weed control or other activities. If you do allocate grant funds for those activites, the message will tell you to change it.
4 Project Activities | F | Message "please change" | If the percentage of grants for requested for fencing (F30) is more than the total cost of fencing (J30) then the following message will appear: Error - fencing grant funds exceed 50% of total fencing cost. Please change the costs paid by each funding source so that fencing grant funds do not exceed 50% of the total fencing cost" | Grant funds must not exceed 50% of the total cost of the fence and may only be used to pay towards fencing costs that are equivalent to what a standard stock fence would cost.

## 3_CarbonProject_
Table A Planting sites and properties/characteristics.
Planting site(s) | Area (ha) | Stems per ha | Target canopy % | Plant community type(s) (PCTs) | Description
A | 7.5 | 400 | 25 | PCT 277: Blakelys Red Gum – Yellow Box grassy tall woodland of the NSW South Western Slopes Bioregion | 125 m wide corridor running 620 m east-west across the centre of the property, excluding the area around an existing tree. PCT 227 is associated with box gum woodland, is the likely PCT prior to clearing, and will provide suitable habitat for the target species.
B | 5 | 400 | 25 | As above | 90 m wide corridor running 700 m north-south along the western boundary, excluding areas around several existing remnant trees. See above comment for PCT 277.
Total | 12.5

## 4_ProjectActivities
Select an option from the drop down menu. This is needed for the budget in 8_Budget to calculate automatically. | Provide details and a description. You can combine information for different planting sites, each site does not need its own line. You can add rows to the tables. |  |  |  | The costs in column F may be paid for by a combination of different sources: grant funds, cash contribution, in-kind or third part contribution. Enter the how much each source is paying for. The total values will automatically update in 8_Budget. Cells that are shaded grey shaded will automatically fill in, you can not edit them. Note that the application form asks for a total in-kind and a total cash so if some of the third party contribution is in cash, keep a note of that on the side. |  |  |  | Enter the full amount of the costs listed in column A. | Include any assumptions or comments, for example if a fencing costs is calculated per meter.
Table B Revegetation method(s) of your Living Carbon project.
Revegetation method | Planting sites | Number of stems | Description and reasons |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
Tube stock | A | 3000 | Quality tubestock is locally available for this relatively small planting project and will likely establish better than direct seeding due to significant weed pressure. 400 stems/ha x 7.5 ha |  | 7500 |  |  |  | 7500 | $2.50/stem x 3000 stems
Tube stock | B | 2000 | 400 stems/ha x 5.0 ha |  | 5000 |  |  |  | 5000 | $2.50/stem x 2000 stems
0
0
0
0
Total | N/A | 5000 | N/A |  | 12500 | 0 | 0 | 0 | 12500
[5 empty] | 12500 | 0
Table C Site preparation activities of the project
Site preparation activity | Planting site(s) | Length (m) or area (ha) | Description and reasons |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
Weed control | A & B | 12.5 ha | Biomass reduction by crash grazing to reduce biomass before ripping and spraying. | [5 empty] | 0 | No cost to move cattle into and out of the site
Soil preparation | A & B | 12.5 ha / 25,000 m | Ripping is the most cost-effective method for preparing both sites, totalling 25,000m with rows 5m apart, before spraying. |  | 11000 |  |  |  | 11000 | Best of 3 contractor quotes ($400/km x 25km + $1000 travel/float/hygiene)
Weed control | A & B | 12.5 ha | Spray Glyphosate on 1 m wide strips along the rip lines one month before planting, to help control weed competition after planting. |  |  | 2500 |  |  | 2500 | 25km x 1km/h x $80/h labour & equipment ($2000) + $100 labour for equipment prep/cleaning + $400 chemical
0
0
Note: grant funds to fund soil preparation (ripping, augering or similar activities). Other activities such as weed control, removal of biomass, and pest control are ineligible grant expenditure. |  |  |  |  | 11000 | 2500 | 0 | 0 | 13500
[5 empty] | 11000 | 2500
Table D: Fencing materials and labour
Materials or labour | Planting site(s) | Length (m) | Description and reason |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
Fencing materials | A | 870 | Fencing wire & posts for new stock fence along the north, east and west side of Site A |  | 4350 |  |  |  | 4350 | Best of 3 contractor quotes for standard stock fence materials ($5000/km)
Fencing materials | B | 700 | Fencing wire & posts for new stock fence along the eastern side of Site B |  | 3500 |  |  |  | 3500 | As above
Fencing materials |  |  | New gate and stays added to existing fence between Site A and B to provide vehicle and stock access between the north and south paddocks (because the existing gate in that fence will now be within planting site B) + 1 new gate to each of Sites A and B |  | 650 |  |  |  | 650 | 3 gates and materials
Fencing labour | A & B |  | Fencing labour and equipment by the landowner as in-kind |  |  |  | 8500 |  | 8500 | Est. 150 hours general fence (~10m/h) + 20 hours for stays = 170 h @ $50/h labour & equipment use
0
0
Grant funds must not exceed 50% of the total cost of the fence and may only be used to pay towards fencing costs that are equivalent to what a standard stock fence would cost. |  |  |  |  | 8500 | 0 | 8500 | 0 | 17000
[5 empty] | 8500 | 8500 |  |  | 17000
|  |  |  | Percent of grants funds out of total fencing cost: | 50%
Table E Tree protection materials and labour
Tree protection materials | Planting site(s) | Description and reasons (include quantity) |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
Tree protection materials | A & B | 5,000 tree guards (one per plant), 1L cardboard - to protect from rabbits and wind. |  |  | 2000 |  |  |  | 2000 | $100/250 pack delivered x 20 packs
Tree protection materials | A & B | 10,000 stakes (2 per guard), 600mm bamboo – to support tree guards |  |  | 2000 |  |  |  | 2000 | $100/500 pack delivered x 20 packs
Planting labour (including installation of tree guards etc.) | A (all) & B (4ha only | Planting and installing 4,500 tubestock & tree guards, contracted labour. |  |  | 9000 |  |  |  | 9000 | $2/stem x 4500 stems
Planting labour (including installation of tree guards etc.) | B (1ha only) | Planting and installing 500 tubestock & tree guards, 50 hours volunteer labour (Landcare event, 20 people x 2.5 h each). | [5 empty] | 2000 | 2000 | $40/h x 50h (10 plants per person-hour)
0
0
Note: equipment such as post hole diggers, mallets (for putting in stakes) and watering equipment, are ineligible grant expenditure. |  |  |  |  | 13000 | 0 | 0 | 2000 | 15000
[5 empty] | 13000 | 2000
Table F: Maintenance and monitoring of planting project
Maintenance and monitoring | Planting site(s) | Description and reasons |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions (Cost per meter)
Initial maintenance as per plan | A & B | Soil moisture - Monitor as per schedule and arrange watering if cost:benefit assessment indicates it is worthwhile |  |  |  |  | 500 |  | 500 | $100 labour x 5 times
Initial maintenance as per plan | A & B | Tree guards - Monitor as per schedule and repair/replace as needed |  |  |  |  | 1500 |  | 1500 | $100 labour x 4 times monitoring + $1100 to replace guards/stakes
Initial maintenance as per plan | A & B | Survival rate - Monitor as per schedule and if likely to drop below 80% will need to order more plants and replace dead ones |  |  |  |  | 1000 |  | 1000 | $100 labour x 2 times monotoring + $800 to replace 200 trees @ $4 each
Initial maintenance as per plan | A & B | Weed control - Regularly monitor and control as required to reduce competition |  |  |  |  | 10000 |  | 10000 | Expect will need two careful spot-spray follow up controls @ ~$5000 each
Initial monitoring and report | A & B | Take photos, collect data and prepare reports for Living Carbon grant |  |  |  |  | 2000 |  | 2000 | 4 reports @ $500 labour each
0
0
0
0
[5 empty] | N/A |  |  |  | 0
Note: grant funds cannot be spent on monitoring and maintenance. These activities will need to be fully paid for by co-contribution to the grants. |  |  |  |  | N/A | 0 | 15000 | 0 | 15000
[5 empty] | N/A | 15000
The Table below is not in your planting plan. It is included here so that Administration costs calculate in the 8_Budget. The grant default costs are pre-written for you. You can add more details or activity lines if that is helpful for you.
Administration activity | Description (specific of what it is) |  |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions (Cost per meter)
ACCU Scheme and Accounting for Nature (AfN) costs | All Living Carbon grant projects will receive a set amount of $5000 for ACCU Scheme and AfN costs. No more can be requested. (You could break this down into more detail) |  |  |  | 5000 | 4000 | 1000 |  | 10000 | $1,000 in landholder's time to coordinate; $9,000 for expert contractor
Other admin | None |  |  |  | 0 | 0 | 1000 | 0 | 1000 | Time spent with support officer, developing case studies, doing surveys, etc
0
0
0
[5 empty] | 5000 | 4000 | 2000 | 0 | 11000
[5 empty] | 5000 | 6000

## 5_TargetCobenefits
Table G: Targeted biodiversity co-benefits your project aims to achieve and justification |  |  |  |  | Table H: Species list, diversity and abundance of predicted species to be planted
Type (flora, fauna, TEC) | Common name | Scientific name | Status | Justification | # | Flora species (scientific name) | Type (T = Tree, S = shrubs) | Quantity to be planted | Planting areas | Co-benefit contribution (only complete if there is a direct relationship to a planned co-benefit)
TEC | Box-gum Woodland (or White-box) | White Box - Yellow Box - Blakely’s Red Gum Grassy Woodland and Derived Native Grassland in the NSW North Coast, New England Tableland, Nandewar, Brigalow Belt South, Sydney Basin, South Eastern Highlands, NSW South Western Slopes, South East Corner and Riverina Bioregions | Critically Endangered (Cwlth); Endangered (NSW) | SOS actions include, where appropriate, increase woodland patch size and condition, and reconnect fragmented patches using appropriate landscape configurations, plant species and provenances. Associated with PCT 277. | 1 | Acacia dealbata | T | 250 | A&B | BGW
Fauna | Dusky Woodswallow | Artamus cyanopterus cyanopterus | Vulnerable (NSW) | SOS activity to assist recovery includes expand and reconnect smaller patches of open eucalypt forest. Associated with PCT 277. | 2 | Acacia implexa | T | 250 | A&B | BGW
Fauna | Brown Treekeeper (eastern subsprecies) | Climacteris picumnus victoriae | Vulnerable (NSW) | SOS actions include undertaking revegetation, particularly adjacent to woodland remnants and streams, avoiding gaps greater than 100m. Associated with PCT 277. | 3 | Eucalyptus albens | T | 500 | A&B | BGW
[5 empty] | 4 | Eucalyptus blakeyi | T | 500 | A&B | BGW
[5 empty] | 5 | Eucalyptus bridgesiana | T | 250 | A&B | BGW
[5 empty] | 6 | Eucalyptus macrorhyncha | T | 500 | A&B | BGW
[5 empty] | 7 | Eucalyptus polyanthemos | T | 500 | A&B | BGW
[5 empty] | 8 | Eucalyptus rubida | T | 250 | A&B | BGW
[5 empty] | 9 | Acacia buxifolia | S | 250 | A&B
[5 empty] | 10 | Acacia genistifolia | S | 250 | A&B
[5 empty] | 11 | Acacia rubida | S | 250 | A&B
[5 empty] | 12 | Acacia veriniciflua | S | 250 | A&B
[5 empty] | 13 | Banksia marginata | S | 250 | A&B
[5 empty] | 14 | Bursaria spinosa | S | 500 | A&B | BGW
[5 empty] | 15 | Callistemon pallidus | S | 250 | A&B
16
17
Table I: Summary of planting project's diversity, abundance and co-benefits |  |  |  |  | 18
Plant Type | Total type | Quantity to be planted | % of total quantity |  | 19
Trees | 8 | 3000 | 60% |  | 20
Shrubs | 7 | 2000 | 40% |  | 21
Total | 15 | 5000 | 100% |  | 22
Providing biodiversity co-benefit | 9 | 3500 | 70% |  | 23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80

## 7_Time0to18mths
List project activities: 1. Keep activities shaded white; 2. For activities shaded in colour, add rows and list your project's specific activities. For example, replace the row for "Site preparation acitivities" with three rows that have "Spray one month prior to planting", "Ripping" and "Ground prepation". | Adjust the timeline: Highlight the month or months that the activity will be completed. Change the months to match when your project will occur.
Table K: Project schedule for 18 months of the Living Carbon grant
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Revegetation tasks
Order materials, order plants, book contractors
Site preparation activities (add your activities on separate rows)
Fencing activities (add your activities on separate rows)
Planting activities (add your activities on separate rows)
Maintenance and monitoring activities (add activities)
Carbon and Environmental Accounting
Annual submission to ACCU Scheme + ACCUs issued
(If applicable) Contact method owner if using NV-07 and NV-10
Register Environmental Account (EA) with AfN (Step 2 AfN)
Build Environmental Account (Step 3 AfN)
Certify Environmental Account (Step 4 AfN) (includes audit)
Biodiversity survey/ ecological assessment monitoring |  | B
EA annual certification compliance report and registration
Living Carbon grant admin
Set up monitoring points, budgeting and grant tracking
Complete project case study
Living Carbon surveys |  | 1 | [13 empty] | 2
Living Carbon grant reports |  | 1 |  |  |  | 2 | [5 empty] | 3 | [5 empty] | 4
Monitor and report on stem survival rate 3-6 months after planting

## 7_ProjectDelivery
Add your own activities and months or dates. We've left a few to get you started. | [20 empty] | Add your own and months or dates. We've left a few to get you started.
1- 5 year Monitoring and Activity Schedule | [20 empty] | Table M: Project schedule for 6 to 25 years | [20 empty] | Table L: Project schedule for 1 to 5 years
Monitoring Year 1 - 5 Change activities to suit you | Year 1 2025 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Monitoring - Years 6-25 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Activities | Y1 |  |  |  | Y2 |  |  |  | Y3 |  |  |  | Y4 |  |  |  | Y5 |  |  |  | Y6
Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Add years to this line > | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
Revegetation Activities | [20 empty] | Revegetation Activities
Planting (direct seeding or tubestock) | [20 empty] | Plant survival (all plants) (once per year)
Plant germination (direct or hand seeding) | [20 empty] | Monitoring activities (as needed or scheduled) | [20 empty] | (Change activities to suit you) | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut
Plant survival post planting (tubestock) or post germination (direct seeding) | [41 empty] | Species selection
Monitoring activities | [41 empty] | Seed collection
[21 empty] | Carbon and Environmental Accounting admin | [20 empty] | Plant propagation
Carbon and Environmental Accounting admin | [20 empty] | CER reporting, ACCUs issued (chosen every 5 years) | [20 empty] | Site preparation
CER reporting, ACCUs issued (as frequently as 6 months to 5 years) | [20 empty] | EA certification compliance report and registration, (once per year) | [20 empty] | Plant installation
Environmental Account certification compliance report and registration | [20 empty] | Maintain EA (data colllection, audit, certify) | [20 empty] | Direct or hand seeding
Maintain EA every 5 years or less (data colllection, audit, certify) | [41 empty] | Site maintenance
Monitoring
[21 empty] | Consider opportunities to share your experiences | [20 empty] | Contingency planting
Threat monitoring | Dependent on site characteristics, and budget. It can be undertaken at any time.
[21 empty] | Threat monitoring | Dependent on site characteristics, and budget. It can be undertaken at any time, recommended annually at the same time as performance monitoring.
Note on V2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be 25 years

## 8_Budget
The budget table automically populates (fills in) cells based on answers in 4_Project Activities. Assumption to do not carry over.
Table N: Planting plan budget
Activity | Activity Costs | Grant funding | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third Party | Total Activity | Assumptions
Site preparation | Soil preparation | 11000 | 0 | 0 | 0 | 11000
Site preparation | Weed control | 0 | 2500 | 0 | 0 | 2500
Site preparation | Other | 0 | 0 | 0 | 0 | 0
Fencing^ | Fencing materials | 8500 | 0 | 0 | 0 | 8500
Fencing | Fencing labour | 0 | 0 | 8500 | 0 | 8500
Revegetation | Direct seeding (seeds and direct seeding) | 0 | 0 | 0 | 0 | 0
Revegetation | Tube stock | 12500 | 0 | 0 | 0 | 12500
Revegetation | Tree protection materials | 4000 | 0 | 0 | 0 | 4000
Revegetation | Planting labour (including installation of tree guards etc.) | 9000 | 0 | 0 | 2000 | 11000
Maintenance & Report | Initial maintenance as per plan | 0 | 0 | 13000 | 0 | 13000
Maintenance & Report | Initial monitoring and report | 0 | 0 | 2000 | 0 | 2000
Admin | ACCU Scheme and Accounting for Nature (AfN) costs | 5000 | 4000 | 1000 | 0 | 10000
Admin | Other admin | 0 | 0 | 1000 | 0 | 1000
Sub total |  | 50000 | 6500 | 25500 | 2000 | 84000
Total |  | 50000 | 34000 |  |  | 84000
^ (max 50% of total grant cost or total fencing costs)
Fencing grant costs do not exceed 50% of the total fencing cost |  | Yes - no changes needed
Fencing grant costs do not exeed 50% of total grant request |  | Yes - no changes needed

## 0_Contractor
For your use only, do not include this in your planting plan.
Contractors or partners with capacity to service proposed revegetation
Contractors or partners with capacity to service proposed revegetation
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)