## ReadmeFirst
Department of Climate Change, Energy, the Environment and Water (DCCEEW), NSW
Planting Plan Workbook - Instructions
To be used when completing your planting plan for your Living Carbon grant application.
About this Workbook
This planting plan workbook contains blank and pre-formatted versions of each table that you need to complete in your planting plan. It is recommended that you fill out each table in the workbook, specifically those containing formulas. You can then copy and paste the completed tables into your planting plan. Note: When copying and pasting tables from the workbook into your planting plan, only copy over the contents and not the formulas. Do this by: 1. selecting/highlighting the completed table in the workbook 2. right click and select ‘Copy’ 3. go your planting plan, place the cursor where you want to paste/insert the table and right click on it, 4. select “Paste Special” 5. select the first icon on the left to “Keep Source Formatting (K)” There is one sheet (the coloured tabs at the bottom) for every section of your planting plan except for the schedules/timelines which are divided across two sheets. See the sections and their corresponding tables below.
| Guide Section | Worksheet tab | Tables included
| Section 3 | 3_CarbonProject | Table A - Planting sites and properties/characteristics.
| Section 4 | 4_ProjectActivities | Table B to Table F - Planting method, Site preparation, Fencing, Planting materials, Maintenance and reporting Also, Admin (optional for workbook budget only)
| Section 5 | 5_TargetCobenefits | Table G to Table I - Target co-benefits; Species list, diversity and abundance of predicted species to be planted; Summary of planting diversity and abundance
| Section 7 | 7_Time0to18mths 7_ProjectDelivery | Table K - Project schedule for 18 months of the Living Carbon grant Table L and Table M - Project schedules for 1 to 5 years and 6 to 25 years
| Section 8 | 8_Budget 0_Contractor | Budget overall Optional for applicant only to record contractors
Instructions
> Follow the prompts at the top of each sheet and in the guide to complete the workbook. > Parts of the workbook that contain formulas or drop down menus are locked, which means you can not change them. This is to prevent you accidnetally deleting them. > You can add rows to all tables except the 8_Budget sheet, you can not add columns > If you are unsure of why some cells become automatically shaded or what an error messsage means, refer to Workbook rules below.
Disclaimer: using this workbook is optional, not mandatory. The workbook will not be submitted as part of the Living Carbon grant application. All efforts have been made to ensure formulas and figures in the workbook deliver accurate figures. However, we do not guarantee the accuracy of the numbers and we expect anyone using it to double-check their numbers prior to including them in the planting plan.
Applicants do not need to read or review this. It has been noted here, out of interest and so that you can see what the rules are if you use the Worbook long term.
Sheet | Column(s) | Type | Rule | Explanation
4 Project Activities | A and F | Format | If "Weed Control" or "Other" is entered into a cell in column A "Activity", then the cell on the same row in column F "Grant", will go grey. | Grant funds can not be used for weed control or other activities.
4 Project Activities | A, E, F | Message "please change" | If "Weed Control" or "Other" is entered into a cell in column A "Activity", and a number more than $0 is entered into column F "Grant", then this message will appear "Please change grey cell to N/A: because weed control and other is inelgibile grant expenditure". | You can not use grant funds to pay for weed control or other activities. If you do allocate grant funds for those activites, the message will tell you to change it.
4 Project Activities | F | Message "please change" | If the percentage of grants for requested for fencing (F30) is more than the total cost of fencing (J30) then the following message will appear: Error - fencing grant funds exceed 50% of total fencing cost. Please change the costs paid by each funding source so that fencing grant funds do not exceed 50% of the total fencing cost". | Grant funds must not exceed 50% of the total cost of the fence and may only be used to pay towards fencing costs that are equivalent to what a standard stock fence would cost.
8 Budget | A, row 21 | Message "please change" or "no change needed: | Fencing grant costs do not exceed 50% of the total fencing cost. | As above
8 Budget | A, row 22 | Message "please change" or "no change needed: | Fencing grant costs do not exceed 50% of the total grant cost. | Grant funds for fencing costs must not exceed 50% of the total grant reuqest.

## 3_CarbonProject_
Table A Planting sites and properties/characteristics
Planting site(s) | Area (ha) | Stems per ha | Target canopy % | Plant community type(s) (PCTs) | Description
Total | 0 | N/A | N/A

## 4_ProjectActivities
Select an option from the drop down menu. This is needed for the budget in 8_Budget to calculate automatically. | Provide details and a description. You can combine information for different planting sites, each site does not need its own line. You can add rows to the tables. To do this: 1) select the last empty row of the table e.g. row 9 of the Table B 2) right click and select the cursor on "Insert" 3) click on "Insert row above". |  |  |  | The costs in column F may be paid for by a combination of different sources: grant funds, cash contribution, in-kind or third part contribution. Enter the how much each source is paying for. The total values will automatically update in 8_Budget. Cells that are shaded grey shaded will automatically fill in, you can not edit them. Note that the application form asks for a total in-kind and a total cash so if some of the third party contribution is in cash, keep a note of that on the side. |  |  |  | This column will calculate automatically with the total cost of the activity. | Include any assumptions or comments, for example if a fencing costs is calculated per meter, or if third party contribution is cost.
Table B Revegetation method(s) of your Living Carbon project.
Revegetation method | Planting sites | Number of stems | Description and reasons |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
0
0
0
0
0
0
Total | N/A | 0 | N/A |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0
Table C Site preparation activities of the project
Site preparation activity | Planting site(s) | Length (m) or area (ha) | Description and reasons |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
0
0
0
0
0
Note: grant funds to fund soil preparation (ripping, augering or similar activities). Other activities such as weed control, removal of biomass, and pest control are ineligible grant expenditure. |  |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0
Table D: Fencing materials and labour
Materials or labour | Planting site(s) | Length (m) | Description and reason |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
0
0
0
0
0
0
Grant funds must not exceed 50% of the total cost of the fence and may only be used to pay towards fencing costs that are equivalent to what a standard stock fence would cost. |  |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0
|  |  |  | Percent of grants funds out of total fencing cost: | #DIV/0! | #DIV/0!
Table E Tree protection materials and labour
Tree protection materials | Planting site(s) | Description and reasons (include quantity) |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions or comments
0
0
0
0
0
0
0
0
Note: equipment such as post hole diggers, mallets (for putting in stakes) and watering equipment, are ineligible grant expenditure. |  |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0
Table F: Maintenance and monitoring of planting project
Maintenance and monitoring | Planting site(s) | Description and reasons |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions (Cost per meter)
0
0
0
0
0
0
0
0
0
[5 empty] | N/A |  |  |  | 0
Note: grant funds cannot be spent on monitoring and maintenance. These activities will need to be fully paid for by co-contribution to the grants. |  |  |  |  | N/A | 0 | 0 | 0 | 0
[5 empty] | N/A | 0
The Table below is not in your planting plan. It is included here so that Administration costs calculate in the 8_Budget. The grant default costs are pre-written for you. You can add more details or activity lines if that is helpful for you.
Administration activity | Description (specific of what it is) |  |  |  | Grant funds | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third party cash or in-kind contribution | Total line cost | Assumptions (Cost per meter)
0
0
0
0
0
0
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0

## 5_TargetCobenefits
Table G: Targeted biodiversity co-benefits your project aims to achieve and justification |  |  |  |  | Table H: Species list, diversity and abundance of predicted species to be planted
Type (flora, fauna, TEC) | Common name | Scientific species name (N/A for TECs) | Status | Justification | # | Flora species (scientific name) | Type (T = Tree, S = shrubs) | Quantity to be planted | Planting areas | Co-benefit contribution (only complete if there is a direct relationship to a planned co-benefit)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Table I: Summary of planting project's diversity, abundance and co-benefits |  |  |  |  | 17
Plant Type | Total type | Quantity to be planted | % of total quantity |  | 18
Trees | 0 | 0 | #DIV/0! |  | 19
Shrubs | 0 | 0 | #DIV/0! |  | 20
Total | 0 | 0 | #DIV/0! |  | 21
Providing biodiversity co-benefit | 0 | 0 | #DIV/0! |  | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80

## 7_Time0to18mths
On the left hand side, list project activities: 1. Keep activities shaded white; 2. For activities shaded colour, add rows to list your specific activities. For example, replace the row for "Site preparation acitivities" with three rows: "Spray one month prior to planting", "Ripping" and "Ground preparation". On the right, adjust the timeline: Highlight which month/s the activity will be completed. Change the calendar months to match when your project will occur.
Table K: Project schedule for 18 months of the Living Carbon grant
Project month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Calendar month:
Revegetation tasks
Order materials, order plants, book contractors
Site preparation activities (add your activities on separate rows)
Fencing activities (add your activities on separate rows)
Planting activities (add your activities on separate rows)
Maintenance and monitoring activities (add activities)
Carbon and Environmental Accounting
Annual submission to ACCU Scheme + ACCUs issued
(If applicable) Contact method owner if using NV-07 and NV-10
Register Environmental Account (EA) with AfN (Step 2 AfN)
Build Environmental Account (Step 3 AfN)
Certify Environmental Account (Step 4 AfN) (includes audit)
Biodiversity survey/ ecological assessment monitoring |  | B
EA annual certification compliance report and registration
Living Carbon grant admin
Set up monitoring points, budgeting and grant tracking
Complete project case study
Living Carbon surveys |  | 1 | [13 empty] | 2
Living Carbon grant reports |  | 1 |  |  |  | 2 | [5 empty] | 3 | [5 empty] | 4
Monitor and report on stem survival rate 3-6 months after planting

## 7_ProjectDelivery
Add your own activities and months or dates. We've left a few to get you started. | [20 empty] | Add your own and months or dates. We've left a few to get you started.
1- 5 year Monitoring and Activity Schedule | [20 empty] | Table M: Project schedule for 6 to 25 years | [20 empty] | Table L: Project schedule for 1 to 5 years
Monitoring Year 1 - 5 Change activities to suit you | Year 1 2025 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Monitoring - Years 6-25 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Activities | Y1 |  |  |  | Y2 |  |  |  | Y3 |  |  |  | Y4 |  |  |  | Y5
Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Add years to this line > | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
Revegetation Activities | [20 empty] | Revegetation Activities | [20 empty] | (Change activities to suit you) | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut | Win | Spr | Sum | Aut
Planting (direct seeding or tubestock) | [20 empty] | Plant survival (all plants) (once per year) | [20 empty] | Species selection
Plant germination (direct or hand seeding) | [20 empty] | Monitoring activities (as needed or scheduled) | [20 empty] | Seed collection
Plant survival post planting (tubestock) or post germination (direct seeding) | [41 empty] | Plant propagation
Monitoring activities | [41 empty] | Site preparation
[21 empty] | Carbon and Environmental Accounting admin | [20 empty] | Plant installation
Carbon and Environmental Accounting admin | [20 empty] | CER reporting, ACCUs issued (chosen every 5 years) | [20 empty] | Direct or hand seeding
CER reporting, ACCUs issued (as frequently as 6 months to 5 years) | [20 empty] | EA certification compliance report and registration, (once per year) | [20 empty] | Site maintenance
Environmental Account certification compliance report and registration | [20 empty] | Maintain EA (data colllection, audit, certify) | [20 empty] | Monitoring
Maintain EA every 5 years or less (data colllection, audit, certify) | [41 empty] | Contingency planting
Consider opportunities to share your experiences
Threat monitoring | Dependent on site characteristics, and budget. It can be undertaken at any time.
[21 empty] | Threat monitoring | Dependent on site characteristics, and budget. It can be undertaken at any time, recommended annually at the same time as performance monitoring.

## 8_Budget
The budget table automically populates (fills in) cells based on answers in 4_Project Activities. Assumption to do not carry over.
Table N: Planting plan budget
Activity | Activity Costs | Grant funding | Landowner cash co-contribution ($) | Landowner in-kind ($ equivalent) | Third Party | Total Activity | Assumptions
Site preparation | Soil preparation | 0 | 0 | 0 | 0 | 0
Site preparation | Weed control | 0 | 0 | 0 | 0 | 0
Site preparation | Other | 0 | 0 | 0 | 0 | 0
Fencing^ | Fencing materials | 0 | 0 | 0 | 0 | 0
Fencing | Fencing labour | 0 | 0 | 0 | 0 | 0
Revegetation | Direct seeding (seeds and direct seeding) | 0 | 0 | 0 | 0 | 0
Revegetation | Tube stock | 0 | 0 | 0 | 0 | 0
Revegetation | Tree protection materials | 0 | 0 | 0 | 0 | 0
Revegetation | Planting labour (including installation of tree guards etc.) | 0 | 0 | 0 | 0 | 0
Maintenance & Report | Initial maintenance as per plan | 0 | 0 | 0 | 0 | 0
Maintenance & Report | Initial monitoring and report | 0 | 0 | 0 | 0 | 0
Admin | ACCU Scheme and Accounting for Nature (AfN) costs | 0 | 0 | 0 | 0 | 0
Admin | Other admin | 0 | 0 | 0 | 0 | 0
Sub total |  | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 |  |  | 0
^ (max 50% of total grant cost or total fencing costs)
Fencing grant costs do not exceed 50% of the total fencing cost |  | Yes - no changes needed
Fencing grant costs do not exeed 50% of total grant request |  | Yes - no changes needed

## 0_Contractor
For your use only, do not include this in your planting plan.
Contractors or partners with capacity to service proposed revegetation
Contractors or partners with capacity to service proposed revegetation
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)
Contractor Name
Works to be contracted for
Relevant experience undertaking revegetation projects
Availability to undertake proposed tasks (list relevant equipment)